## Masters Feedback
Main Module | Sub Module | Sub-Tabs | Task | Sub-Task | Required | Reason if any functionality not needed | Data | Where to source Data | Change Required | Remark by Cyclone Pharma
Miscallaneous | Material Types | [7 empty] | Need to check if we need to add more Material Type masters | Done
[9 empty] | Material Type and Material Sub-Type naming convention should be standardised | Done
[9 empty] | Material Type and Material Sub-Type should have a audit log, electronic signature required | Done
[9 empty] | Any masters or configuration should have Electronic Signature supported. | Done
| FG Type | [7 empty] | FG Types --> Product Nature --> Product Name | Done
[9 empty] | FG Types --> When we try to save Duplicate record, please add a pop-up to show the user that the record already exists | Done
[9 empty] | FG Types - -> Add option to edit a record whereever applicable | We Can't give you option to edit a record
[9 empty] | FG -->Change from FG to FP | Done
| UOM | [7 empty] | Able to control the master record.
| Grade | [7 empty] | Table shows unit instead of Grades, Grades shown in Chemical Master is didfferent, need to check how grades are populated. | Done
[9 empty] | Pharmacopei name not required, so delete | Need to Discuss with Mr. Sachin
| Tax/VAT |  |  |  | No | We will still keep as it might be needed in Finance module |  |  | Mark Grade field as mandatory | Done
| Storage Condition | [7 empty] | Applicbility of Storage Conditions, to be revisited | It comes from Master But it totally Depends on U that u want to use it or want to skip
Test | [8 empty] | We need to define the different Test Types and share it with PLGMP
[9 empty] | Need to clarify when we add a New Test Method, if the Test Method number is added manually or autogenerated | Manually
[9 empty] | Character limit requested in all Text Field | No
[9 empty] | Test Method --> Associate Document name is incorrectly spelt | Done
[9 empty] | Confirm what is the purpose of General Scope | Need to check in Format
[9 empty] | Associate Document - Should follow some sort order logic | Done
[9 empty] | Associate Document - Validation to not add duplication entries | Done
[9 empty] | Deinifation Spelling is incorrect | Done
[9 empty] | Change Short Name to Term and Full name to definition | Done
[9 empty] | Safety --> Insert File / Image does not open the source, it should support oopen source directory | External Link Pushing in Our Software Not Allowed
[9 empty] | Equipment / Instructions - No need for Make and Capacity | Done
[9 empty] | Any blank field on the application should display as N/A it is a GMP requirement | Done
[9 empty] | Mobile Phase masters should be a separate module | Can be Done in 3-4 Days
[9 empty] | Some of the Testing Instructions need some of the steps that need to capture weight during different steps of the testing proceudre, we need to accommodate that FM - 105 | Can be Done in 3-4 Days
[9 empty] | naming change from Documentation to Quality Report | Done
[9 empty] | Introduce a new section called Training Requirements in the Test Method Form | Please Explain In Detail ??
[9 empty] | Test Method approval to follow the SOP approval model | Can be Done in 3-4 Days
Miscallaneous | [8 empty] | have a draft state of Test Method just like the SOP format , check reject | Can be Done in 3-4 Days
Product | [8 empty] | Move FG types needs to be moved RM, PM, General, In process, Consumable | Done
BOM | [8 empty] | Need to reconfirm that we will have eveer Intermediate Product applicability | It has been Removed
[9 empty] | Country and Short Code applicablity if more than one country distribution is needed (revisit the functionality and logic) | It Has been Removed from Master
Master Forumala Revision Should support only one entry and the effecitive date should
Master Checklist | [8 empty] | New Checklist --> Populate all masters | Mr. Sachin will explain this in Meeting
Clarification on what module means, may be name it as activity
[9 empty] | How does | Mr. Sachin will explain this in Meeting
Standard Master | [8 empty] | Standard Weight to be managed for Equipment Masters